## Summary Dashboard
AI DATING PROFILE COACH — PROJECT ESTIMATION
Version 1.0 ¦ Based on SRD V1 ¦ Estimates in Story Points & Hours
| TOTAL STORY POINTS |  | TOTAL EST. HOURS |  | MODULES |  | SPRINTS (2-WK)
| 464 |  | 34.8456 |  | 17 |  | 7
| Module | Category | Story Pts | Low Hrs | High Hrs | Avg Hrs | Priority
1 | Authentication & User Management | Infrastructure | 13 | 16 | 24 | 20 | Must Have
2 | Onboarding Flow & Interview UI | Frontend | 21 | 32 | 48 | 40 | Must Have
3 | Interview Agent (AI) | AI / Backend | 34 | 48 | 72 | 60 | Must Have
4 | Dynamic Question Engine | AI / Backend | 21 | 32 | 48 | 40 | Must Have
5 | Personality Extraction Agent | AI / Backend | 13 | 20 | 30 | 25 | Must Have
6 | Prompt Library & DB Setup | Backend / DB | 8 | 10 | 16 | 13 | Must Have
7 | Prompt Recommendation Engine | AI / Backend | 13 | 16 | 24 | 20 | Must Have
8 | Prompt Answer Generator | AI / Backend | 13 | 16 | 24 | 20 | Must Have
9 | Bio & Tagline Generator | AI / Backend | 8 | 10 | 16 | 13 | Must Have
10 | Photo Recommendation Engine | AI / Backend | 8 | 10 | 16 | 13 | Must Have
11 | Profile Composer Service | Backend | 8 | 12 | 20 | 16 | Must Have
12 | Hinge-Style Profile Preview UI | Frontend | 21 | 32 | 48 | 40 | Must Have
13 | Copy, Export & Regenerate UI | Frontend | 8 | 10 | 16 | 13 | Should Have
14 | MongoDB Schema & Data Layer | Infrastructure | 8 | 12 | 18 | 15 | Must Have
15 | API Layer & Security | Infrastructure | 13 | 16 | 24 | 20 | Must Have
16 | Testing & QA | QA | 13 | 24 | 40 | 32 | Must Have
17 | DevOps & Deployment | DevOps | 5 | 8 | 14 | 11 | Must Have
TOTAL |  |  | 228 | 324 | 498 | 411

## Module Breakdown
MODULE BREAKDOWN — TASK-LEVEL ESTIMATION
# | Module / Task | Description | Category | Story Pts | Low Hrs | High Hrs | Avg Hrs
1. AUTHENTICATION & USER MANAGEMENT
1.1 | Clerk integration & auth setup | Configure Clerk SDK, OAuth providers (Google, Apple), session tokens | Infrastructure | 3 | 4 | 6 | 5
1.2 | Protected route middleware | Validate Clerk tokens on every API route handler | Infrastructure | 2 | 2 | 4 | 3
1.3 | User document creation on first auth | Create MongoDB user record on first successful sign-in | Backend | 2 | 2 | 4 | 3
1.4 | Logout & session invalidation | Implement sign-out flow and token cleanup | Frontend | 1 | 1 | 2 | 1.5
1.5 | Account deletion & data purge | Delete user + all associated MongoDB records | Backend | 3 | 4 | 6 | 5
1.6 | Auth error handling & UX | Error states, feedback messages, redirect flows | Frontend | 2 | 3 | 4 | 3.5
2. ONBOARDING FLOW & INTERVIEW UI
2.1 | Landing page | Marketing page with value prop, CTA, responsive layout | Frontend | 3 | 4 | 8 | 6
2.2 | Chat interface component | Real-time streaming chat UI with message bubbles, typing indicator | Frontend | 5 | 8 | 14 | 11
2.3 | Streaming token rendering | Integrate Vercel AI SDK streaming into chat UI | Frontend | 3 | 4 | 8 | 6
2.4 | Interview progress indicator | Visual progress bar showing personality coverage % | Frontend | 3 | 4 | 8 | 6
2.5 | Session resume UX | Resume paused interview on re-login | Frontend | 3 | 6 | 8 | 7
2.6 | Mobile-responsive layout | Ensure all interview screens work on mobile | Frontend | 4 | 6 | 10 | 8
3. INTERVIEW AGENT (AI)
3.1 | System prompt engineering | Design and iterate Interview Agent system prompt | AI | 5 | 8 | 12 | 10
3.2 | Conversation history management | Pass full or windowed conversation history to LLM on each turn | Backend | 3 | 4 | 6 | 5
3.3 | Follow-up question logic | Prompt engineering to produce contextual follow-ups | AI | 5 | 8 | 12 | 10
3.4 | Streaming API route handler | Next.js route handler with Vercel AI SDK streaming | Backend | 3 | 4 | 8 | 6
3.5 | Message storage (MongoDB) | Save every user/AI message to Messages collection | Backend | 3 | 4 | 6 | 5
3.6 | Interview termination logic | Detect when confidence thresholds are met and close interview | Backend | 5 | 8 | 12 | 10
3.7 | Duplicate question prevention | Track asked questions and filter LLM output | Backend | 5 | 8 | 12 | 10
3.8 | LLM retry & error handling | Exponential backoff, 3 retries, graceful error UX | Backend | 5 | 8 | 10 | 9
4. DYNAMIC QUESTION ENGINE
4.1 | Personality trait map definition | Define all required traits per Hinge prompt; store as config/DB | Backend | 3 | 4 | 8 | 6
4.2 | Trait gap detection logic | After each turn, compute which traits are still missing | Backend | 5 | 8 | 12 | 10
4.3 | Confidence score calculation | Score each category 0-100 after each response | Backend | 5 | 8 | 12 | 10
4.4 | Configurable thresholds | Allow per-category confidence thresholds | Backend | 3 | 4 | 6 | 5
4.5 | Dynamic question selection | Only surface questions that fill identified gaps | AI | 5 | 8 | 10 | 9
5. PERSONALITY EXTRACTION AGENT
5.1 | Extraction prompt design | Prompt engineering to convert chat history to JSON personality profile | AI | 3 | 4 | 8 | 6
5.2 | JSON schema validation | Validate extracted profile against PersonalityProfile schema | Backend | 2 | 4 | 6 | 5
5.3 | PersonalityProfile MongoDB save | Upsert personality profile to PersonalityProfiles collection | Backend | 2 | 2 | 4 | 3
5.4 | Extraction trigger on interview end | Hook extraction agent to interview termination event | Backend | 3 | 4 | 6 | 5
5.5 | Error handling & retry | Handle malformed LLM JSON; retry with correction prompt | Backend | 3 | 4 | 6 | 5
6. PROMPT LIBRARY & DB SETUP
6.1 | MongoDB Atlas setup & Mongoose config | Configure Atlas cluster, connection pooling, env vars | Infrastructure | 2 | 2 | 4 | 3
6.2 | PromptLibrary collection & schema | Define Mongoose schema; seed with Hinge prompts + metadata | Backend | 3 | 4 | 8 | 6
6.3 | All other collection schemas | Users, Sessions, Messages, PersonalityProfiles, GeneratedProfiles, Feedback | Backend | 3 | 4 | 6 | 5
7. PROMPT RECOMMENDATION ENGINE
7.1 | Trait-to-prompt matching logic | Algorithm to match personality traits against prompt metadata | Backend | 5 | 8 | 12 | 10
7.2 | Ranking & selection | Rank matched prompts; select top N (configurable, default 3) | Backend | 3 | 4 | 8 | 6
7.3 | API endpoint for recommendations | Route handler exposing recommendation results to pipeline | Backend | 3 | 4 | 6 | 5
7.4 | Unit tests for recommendation logic | Test matching edge cases (missing traits, all traits, etc.) | QA | 2 | 4 | 6 | 5
8. PROMPT ANSWER GENERATOR
8.1 | Prompt answer generation LLM call | Per-prompt LLM call using personality profile + prompt as input | AI | 3 | 4 | 8 | 6
8.2 | Answer quality prompt engineering | Iterate prompts for authentic, creative, on-brand answers | AI | 5 | 8 | 12 | 10
8.3 | Batch generation support | Generate all N selected prompt answers in parallel | Backend | 3 | 4 | 6 | 5
8.4 | Answer storage | Save answers to GeneratedProfiles collection | Backend | 2 | 2 | 4 | 3
9. BIO & TAGLINE GENERATOR
9.1 | Bio generation LLM call | Single LLM call producing bio + description + tagline | AI | 3 | 4 | 8 | 6
9.2 | Bio prompt engineering | Iterate prompts for concise, authentic bios | AI | 3 | 4 | 6 | 5
9.3 | Bio storage | Save to GeneratedProfiles collection | Backend | 2 | 2 | 4 | 3
10. PHOTO RECOMMENDATION ENGINE
10.1 | Trait-to-photo-type mapping | Rule-based mapping (gym -> workout photo, travel -> travel photo) | Backend | 3 | 4 | 8 | 6
10.2 | Caption generation | Generate suggested captions per photo type | AI | 3 | 4 | 6 | 5
10.3 | Photo order logic | Determine optimal photo order based on personality | Backend | 2 | 2 | 4 | 3
10.4 | Photo suggestions storage | Save photo suggestions to PhotoSuggestions / GeneratedProfiles | Backend | 2 | 2 | 4 | 3
11. PROFILE COMPOSER SERVICE
11.1 | Profile assembly logic | Merge bio, prompt answers, photo suggestions into one profile object | Backend | 3 | 4 | 8 | 6
11.2 | GeneratedProfile save | Upsert complete profile object to GeneratedProfiles collection | Backend | 2 | 2 | 4 | 3
11.3 | Profile versioning | Increment version on regeneration; retain history | Backend | 3 | 4 | 6 | 5
11.4 | Composer API endpoint | Route handler that triggers full pipeline and returns profile | Backend | 2 | 2 | 4 | 3
12. HINGE-STYLE PROFILE PREVIEW UI
12.1 | Profile card component | Hinge-style card layout matching real app visual design | Frontend | 5 | 8 | 14 | 11
12.2 | Prompt answer rendering | Display each prompt + answer in Hinge card style | Frontend | 3 | 4 | 8 | 6
12.3 | Photo placeholder & order display | Show photo slots with suggestions and recommended order | Frontend | 3 | 4 | 8 | 6
12.4 | Bio & tagline display | Render bio section matching Hinge layout | Frontend | 3 | 4 | 6 | 5
12.5 | Loading / processing screen | Animated screen during AI pipeline execution | Frontend | 3 | 4 | 6 | 5
12.6 | Framer Motion animations | Transition animations between screens | Frontend | 2 | 4 | 6 | 5
12.7 | Mobile optimization of preview | Ensure Hinge preview works on mobile | Frontend | 2 | 4 | 6 | 5
13. COPY, EXPORT & REGENERATE UI
13.1 | Copy individual prompt to clipboard | One-click copy for each prompt answer | Frontend | 2 | 2 | 4 | 3
13.2 | Regenerate individual section | Trigger re-generation of bio or single prompt without full re-run | Frontend | 3 | 4 | 8 | 6
13.3 | Export full profile | Export as plain text or PDF download | Frontend | 3 | 4 | 6 | 5
14. MONGODB SCHEMA & DATA LAYER
14.1 | Mongoose model definitions | All 8 collection schemas with types, validations, indexes | Backend | 3 | 4 | 6 | 5
14.2 | Index optimization | Compound indexes on userId + session lookups | Backend | 2 | 4 | 6 | 5
14.3 | Data access layer / repository pattern | Centralized DB access functions per collection | Backend | 3 | 4 | 6 | 5
15. API LAYER & SECURITY
15.1 | Auth middleware on all routes | Verify Clerk token on every route handler | Backend | 2 | 2 | 4 | 3
15.2 | Rate limiting | Protect AI endpoints from abuse | Backend | 3 | 4 | 6 | 5
15.3 | Input validation & sanitization | Validate all incoming payloads; prevent injection | Backend | 3 | 4 | 6 | 5
15.4 | Environment variable management | Secure handling of OpenAI keys, DB URIs, Clerk keys | DevOps | 2 | 2 | 4 | 3
15.5 | Error response standardization | Consistent error response format across all endpoints | Backend | 3 | 4 | 6 | 5
16. TESTING & QA
16.1 | Unit tests — backend logic | Jest tests for question engine, extraction, composer | QA | 3 | 6 | 10 | 8
16.2 | Integration tests — API routes | End-to-end route testing with mock LLM responses | QA | 3 | 6 | 10 | 8
16.3 | AI output quality review | Manual review of generated profiles for quality assurance | QA | 3 | 6 | 10 | 8
16.4 | Cross-browser & mobile testing | Test on Chrome, Safari, Firefox; iOS and Android | QA | 2 | 4 | 6 | 5
16.5 | Security audit | API key exposure check, auth bypass testing | QA | 2 | 4 | 6 | 5
17. DEVOPS & DEPLOYMENT
17.1 | Vercel project setup | Configure project, environment variables, domains | DevOps | 1 | 1 | 2 | 1.5
17.2 | CI/CD pipeline | GitHub Actions for lint, test, deploy on merge | DevOps | 2 | 4 | 6 | 5
17.3 | MongoDB Atlas production config | IP allowlist, production cluster, backups, monitoring | DevOps | 2 | 3 | 6 | 4.5
TOTAL (Tasks Only) |  |  |  | 232 | 336 | 552 | 444

## Sprint Plan
SPRINT PLAN — AI DATING PROFILE COACH V1
Sprint | Focus Area | Key Deliverables | Story Points | Est. Hours | Status
Sprint 1 | Foundation & Auth | MongoDB Atlas + Mongoose schemas, Clerk auth setup, protected routes, user creation on sign-up, landing page | 26 | 38 | Planned
Sprint 2 | Interview UI & Agent | Chat interface, Vercel AI SDK streaming, Interview Agent prompt engineering, message storage, session management | 34 | 52 | Planned
Sprint 3 | Dynamic Question Engine | Personality trait map, gap detection, confidence scoring per category, configurable thresholds, duplicate prevention | 21 | 38 | Planned
Sprint 4 | Personality Extraction & Prompt Library | Extraction Agent + JSON validation, PersonalityProfile upsert, PromptLibrary seeding with full metadata | 26 | 42 | Planned
Sprint 5 | Recommendation & Generation Engines | Prompt Recommendation Engine, Prompt Answer Generator (parallel), Bio/Tagline Generator, Photo Recommendation Engine | 42 | 64 | Planned
Sprint 6 | Profile Composer & Preview UI | Profile Composer service, Hinge-style preview UI, photo slot display, bio rendering, loading screen, animations | 34 | 54 | Planned
Sprint 7 | Polish, QA & Deploy | Copy/export/regenerate UI, mobile optimization, full test suite, security audit, CI/CD pipeline, Vercel prod deploy | 26 | 42 | Planned
TOTAL |  |  | 209 | 330

## Assumptions & Notes
ESTIMATION ASSUMPTIONS & NOTES
TEAM & VELOCITY
1 | Sprint Length | 2 weeks (10 working days per sprint)
2 | Team Velocity | 80 hours / sprint — assumes 1 full-stack dev + part-time AI/ML support
3 | Story Point Scale | Fibonacci (1,2,3,5,8,13,21) — 1 SP ~ 1.5-2 hrs average for this project
4 | Hour Range | Low = optimistic path. High = includes iteration, review, and ramp-up
5 | Avg Hours | (Low + High) / 2 — used for planning and sprint allocation
ESTIMATION SCOPE
1 | Scope | Covers all 17 modules defined in SRD V1
2 | Excluded (Post-V1) | AI Photo Rating, Conversation Coach, Profile Roast, Match Prediction, Multi-App Support
3 | AI Prompt Iteration | AI prompt engineering carries ±30% variance; High estimates include 1-2 iteration cycles
4 | QA | Testing estimated separately in Module 16; not double-counted in feature modules
5 | DevOps | Assumes Vercel Pro tier; no self-hosted infrastructure required
RISKS & UNCERTAINTY
1 | GPT-5.5 Latency | Streaming latency may require UX adjustments; buffered in Interview Agent estimates
2 | Prompt Engineering | AI quality iteration is unpredictable — estimates may expand 20-30%
3 | Open Questions | SRD OQ-01 to OQ-07 may add 10-15% overhead once resolved
4 | Third-Party APIs | Clerk and MongoDB Atlas assumed stable; unexpected integration issues not budgeted
5 | Design Handoff | UI estimates assume finalized design specs are ready at sprint start
PRIORITY LEGEND
1 | Must Have | Core V1 scope — required for product launch
2 | Should Have | High value — include if sprint capacity allows
3 | Nice to Have | Deferred to V1.1+ if capacity is constrained